## Sheet1
ID | Actor | Requirement | Story | Task | Priority | Estimated Order of Implementation | Total Estimated Time (Hours of Iteration 1 and 2) | Total Actual Time Spent (Hours of Iteration 1 and 2) | Total Story Points (0, 0.5, 1, 2, 3, 5, 8, 13, 20, 40, 100) | Worked on By | Iteration | Status | Notes
1 | Treasurer | Track club finances. | Treasurer needs to be able to see the club’s current profit. | Create the income statement and add the revenue portion (members payments, any other income that may come). | Medium | 15 | 2 | 1 | 20 | Mohamed Abdulle | 2 | Completed | Income statement automatically displays in the club finances tab when the treasurer logs in
2 |  |  |  | Add the expense portion to the income statement (coach’s payments, hall expenses, any other expenses). |  | 16 | 2 | 2 | 20 | Mohamed Abdulle | 2 | In Progress | Expenses portion has yet to be added to the income statement.
3 |  |  |  | Create a list for the year, logging each month’s profit to compare changes in revenue/expenses in order to find ways to maximize profit. |  | 17 | 3 | – | 40 | – | - | To Be Completed | Task has not been started.
4 |  |  | Treasurer needs a log of any unpaid debt from previous months (i.e. any months the rent for the hall was not paid, or not fully paid, and unpaid coach expenses). | Create a list to log the total amount of unpaid coach expenses and hall expenses for each month, prioritizing the urgency for payment. | High | 13 | 1 | 1 | 13 | Mohamed Abdulle | 2 | In Progress | The treasurer tab displays unpaid debt from previous months, including coach and hall expenses. We did not prioritize urgency for payment. We also need to make the ability to choose the month more dynamic.
5 |  |  | Treasurer needs the current month’s account payables (e.g.members who have paid in advance). | For efficiency, this can be listed in the income statement under revenues. Since there is no mention of a return policy, this can be counted as a revenue as soon as the transaction is completed. | Medium | 14 | 3 | 2 | 13 | Mohamed Abdulle | 2 | Completed | Anyone with a negative balance or has a balance of 0 has paid in advance.
6 | Coach | Log and sort members. | Keep a log of the members. | Create a list of the members who have attended the class, and those who will be attending the class. Each member will have their name, phone number, whether they paid or not, and address. | Medium | 4 | 2 | 3 | 5 | Mohamed Abdulle | 2 | Completed | A table of members is currently being displayed with all the required information.
7 |  |  | Sort the members by their frequency of attendance in the club. Provide a discount based on amount of practices attended. | Using the list of members, organize the members by the amount of times they have attended practice at the club. | Low | 5 | 2 | 1 | 1 | Mohamed Abdulle | 1 | Completed | This functionality is checked every time the coach logs into the system. A discount is applied to the top 10 most attendees.
8 |  |  |  | Based on the frequency level, the member will have a loyalty discount. The top 10 people on the list of most practices attended will 3 receive a complimentary discount of %10 off for one class. This will help ensure member retention. |  | 7 | 3 | 1 | 2 | Taras Kozak | 1 | Completed | This functionality is done automatically. No need for user action required. Penalties and discounts applied on Coach login.
9 |  |  | Sort the members by whether they have paid or not. Provide a discount or charge based on amount of unpaid/paid classes. | Using the list of members, organize the members by the amount of times they paid/not paid. | High | 6 | 2 | 1 | 1 | Mohamed Abdulle | 1 | Completed | A database method has been implemented for the coach to see which members have paid or not.
10 |  |  |  | If the member has not paid more than once, then he will be subject to a penalty fee and possibly exclusion from the group. A reminder will be sent for any member who has skipped at least one payment. |  | 8 | 3 | 3 | 3 | Tony Shao | 1 | Completed | This functionality is updated every time the coach logs into the system.
11 |  |  |  | If the member does not skip a payment for 3 months, he will receive a complimentary discount for 10% off for one class. |  | 10 | 1 | 2 | 2 | Taras Kozak | 1 | Completed | This functionality is updated every time the coach logs into the system.
12 | Coach | User interaction with application. | The coach should be able to communicate to the members about future practices. | Create a user interface where a message can be sent out to all or some members, with details of future practices or changes to any practices. A reminder message can also be sent out for a member who has skipped a payment. | High | 9 | 9 | 7 | 40 | Tony Shao Maitreya Meshram | 2 | Completed | Message user interface for Coach and Member is completed
13 | Treasurer Coach |  | The treasurer should be able to manage coach list and schedule. The coach should be able to manage the members list (i.e. adding or removing) | Create user interfaces for different character to modify the list of participants. And the corresponding character will receive notification upon changes. | Medium | 11 | 3 | 4 | 5 | Tony Shao Maitreya Meshram | 2 | In Progress | Coach and treasurer can manage the member list. The treasurer has a UI to add coaches, but the coach database was not implemented.
14 | Member |  | Members need to be able to schedule and pay for the practice within the app. | Create user interface of payment methods or link to a third party payment method. Treasurer and coach should receive notification of the scheduled practice and received payment with user id, class amount and relative coach. | Medium | 12 | 3 | 2 | 100 | Tony Shao Mohamed Abdulle | 2 | In Progress | In the Payment Tab of membership management, the members balance owed shown. Right next to it is a link to PayPal. The user will be asked to submit a payment through PayPal. Upon next login session, the coach will be notified. The members are not yet able to schedule for practice.
15 | Treasurer Coach Member | Store user data. | Treasurer & coach need to access, update, and delete member's personal and financial information. | Design the database structure. Implement the database and driver and developed the database ultility methods. Develop member tables that insert, update, delete, and query user data through the graphical user interface. | High | 3 | 20 | 24 | 100 | Taras Kozak | 2 | In Progress | Database tables are developed for members; treasurer and coach are able to modify member attributes. Coach and treasurer databases are not yet completed.
16 |  | Interface to interact with application. | Treasurer, coach, and members need an interface to perform and interact with the tasks. | Implement a graphical user interface that provides the interface for the treasurer's tasks, which consists of ID's 1-5, 13; ID's 6-13 for the coach's tasks; ID 14 for the member task. | High | 1 | 14 | 10 | 13 | Tony Shao Maitreya Meshram Mohamed Abdulle Taras Kozak | 2 | Completed | The schedule timeline calendar, creating events, adding new coaches is left to be implemented in the database. Members, treasurer, and coach graphical user interface are completed.
17 |  |  | Login interface that opens the appropiate graphical user interface. | Depending on the username and password, a graphical user interface opens that is tailored to the needed functionality for the treasurers, coach, or member. | High | 2 | 2 | 2 | 5 | Tony Shao Maitreya Meshram Taras Kozak | 1 | Completed | User logs in by entering appropriate username and password which is verified and validated.
18 | Treasurer | Add a coach. | Treasure should be able to add new coaches (create coach user) and assign them to an exercise class. | Create a graphical user interface panel "Add new coach" that accepts coach's personal info, salary, and class they are teaching. | Low | 18 | 4 | 2 | 13 | Maitreya Meshram | 2 | In Progress | The GUI for adding a new coach is done. Coach database needs to be implemented.
Group Members: | [5 empty] | Iterationt 2 | Iteration 1
Tony Shao Maitreya Meshram Mohamed Abdulle Taras Kozak | [5 empty] | Iteration 2 total estimated and actual hours are changed for any IN PROGRESS tasks from iterations 1.